## Burndown Chart
User Story | Story Time | Day1 | Day2 | Day3 | Day4
As a researcher in education in Pakistan | 8 | 2 | 0 | 0 | 0
As a federal policymaker in Pakistan | 8 | 4 | 4 | 2 | 0
As a Twitterverse member | 8 | 7 | 3 | 0 | 0
As a student taking a website application course | 8 | 8 | 6 | 2 | 0
As a student taking a data visualization course | 13 | 11 | 6 | 3 | 0
As a student who is learning about the Scrum framework | 13 | 10 | 7 | 6 | 0
| 58 | 42 | 26 | 13 | 0
Grand Total | 58
Day1 | 42
Day2 | 26
Day3 | 13
Day4 | 0

## Spring Meetings
Sprint1 Standup Meetings
Date/Time | Time | Type
2020-01-11 | 1pm | In Person
2020-01-12 | 2pm | Phone
2020-01-13 | 6pm | In Person
2020-01-14 | 2:30pm | In Person
2020-01-15 | 9am | In Person
Sprint2 Standup Meetings
Date/Time | Time | Type | Points | Remaining | Total
2020-01-16 | 11am | In Person | 16 | 42 | 58
2020-01-17 | 9am | In Person | 32 | 26 | 58
2020-01-18 | 9am | In Person | 45 | 13 | 58
2020-01-19 | 4pm | In Person | 58 | 0 | 58